## Sheet1
CloudCare Medical – ISO 27001 Gap Assessment
Control Area | ISO27001 Domain | Current Status | Gap Identified | Risk Level | Recommendation | Responsible Owner | Target Date
Access Control | Access Management | Partial | MFA not enforced for all users | High | Implement mandatory MFA across all systems | IT Security Team | Q3 2026
Password Management | Identity Security | Implemented | Password review schedule not documented | Medium | Establish password review procedure | IT Team | Q2 2026
User Account Reviews | Access Governance | Partial | Dormant accounts not reviewed regularly | High | Perform quarterly access reviews | Compliance Team | Q3 2026
Vendor Risk Management | Supplier Security | Partial | No formal vendor assessment workflow | High | Create vendor risk assessment process | Governance Team | Q3 2026
Incident Response | Security Incident Management | Implemented | No tabletop incident exercises conducted | Medium | Schedule annual incident response testing | Security Team | Q4 2026
Asset Inventory | Asset Management | Partial | Several cloud assets undocumented | High | Maintain centralised asset inventory | Infrastructure Team | Q2 2026
Backup Management | Business Continuity | Implemented | Backup restoration testing incomplete | Medium | Conduct quarterly recovery testing | Infrastructure Team | Q3 2026
Encryption Controls | Cryptography | Partial | Encryption standards inconsistent | High | Standardise encryption requirements | Security Engineering | Q3 2026
Data Retention | Information Lifecycle | Partial | Retention periods undefined for some records | Medium | Create formal retention schedule | Compliance Team | Q2 2026
Data Classification | Information Governance | Implemented | Staff awareness training incomplete | Medium | Conduct classification awareness training | HR & Security Team | Q2 2026
Security Awareness Training | Human Resource Security | Partial | Training completion tracking absent | Medium | Implement training monitoring dashboard | HR Department | Q3 2026
Logging & Monitoring | Monitoring Activities | Partial | Security logs retained inconsistently | High | Define standard log retention periods | SOC Team | Q3 2026
Vulnerability Management | Technical Security | Partial | Vulnerability scans not scheduled regularly | High | Introduce monthly vulnerability scanning | Security Operations | Q2 2026
Patch Management | System Maintenance | Partial | Critical patch timelines undefined | High | Implement patch management policy | IT Operations | Q2 2026
Mobile Device Security | Endpoint Protection | Partial | BYOD controls not documented | Medium | Develop mobile device security standard | IT Governance | Q3 2026
Cloud Security | Cloud Governance | Partial | Cloud configuration reviews inconsistent | High | Conduct periodic cloud security reviews | Cloud Security Team | Q3 2026
Physical Security | Physical & Environmental Security | Implemented | Visitor logging process manual only | Low | Introduce digital visitor tracking | Facilities Team | Q4 2026
Business Continuity Planning | Operational Resilience | Partial | Recovery objectives not fully documented | High | Define RTO and RPO requirements | Business Continuity Team | Q3 2026
Third-Party Access | Supplier Access Control | Partial | External user access approvals undocumented | High | Formalise third-party access approval process | Compliance Team | Q2 2026
Audit Management | Internal Audit | Partial | Audit evidence stored inconsistently | Medium | Centralise audit documentation storage | Governance Team | Q3 2026
Risk Management | Risk Governance | Implemented | Risk reviews not scheduled consistently | Medium | Conduct quarterly risk review meetings | Risk Management Team | Q2 2026
Secure Disposal | Media Handling | Partial | Disposal verification records incomplete | Medium | Maintain disposal certificates and logs | IT Asset Team | Q3 2026
Remote Access Security | Network Security | Partial | VPN monitoring limited | High | Enhance VPN logging and monitoring | Network Security Team | Q2 2026
Data Loss Prevention | Data Protection | Partial | DLP controls not implemented organisation-wide | High | Deploy enterprise DLP solution | Security Engineering | Q4 2026
Compliance Reporting | Regulatory Compliance | Partial | GDPR compliance reporting manual | Medium | Automate compliance reporting workflows | Compliance Officer | Q4 2026